## Health and Rollback Tests
ID | Test case Description | Test case Procedure | Expected Result | Actual Result | Result | Test Date
DHR-TC01 | Return a healthy response when the inference service is ready | 1. Mount the existing health router in an isolated TestClient. 2. Set INFERENCE_BACKEND=llama_server and disable the model-skip flag. 3. Mock a successful model health response. 4. Request GET /api/health. | HTTP 200 with status=ok, inference_backend=llama_server, and model_ready=true. | Isolated route returned HTTP 200 and the exact expected JSON. The model HTTP request was mocked; no deployed endpoint was contacted. | Pass | 2026-10-29
DHR-TC02 | Return an unhealthy response when the inference service is unreachable | 1. Use the isolated health router with model checks enabled. 2. Make the model HTTP dependency raise ConnectError. 3. Request GET /api/health. | HTTP 503 with detail.status=starting and detail.model_ready=false. | Isolated route returned HTTP 503 with the expected detail object. Dependency unavailability was simulated, not induced on a deployment. | Pass | 2026-10-29
DHR-TC03 | Reject an unsupported inference backend as unhealthy | 1. Set an unsupported INFERENCE_BACKEND in the isolated router environment. 2. Disable the model-skip flag. 3. Request GET /api/health. | HTTP 503 and model_ready=false; the health handler must not report readiness for an unsupported backend. | Isolated route returned HTTP 503 and model_ready=false. This tests handler behavior, not full startup configuration validation. | Pass | 2026-10-29
DHR-TC04 | Record the component last-good revision after successful smoke validation | 1. Execute smoke-and-rollback.sh with a successful curl fixture and DEPLOY_UNITS=backend. 2. Capture fixture AWS calls and script exit code. 3. Check whether a remote rollback command was requested. | Exit 0; request one Parameter Store update for the backend last-good key using the current SHA; do not request rollback. | Script exited 0 and requested exactly one backend key update with the fixture current SHA. No rollback command was requested. AWS persistence was not tested. | Pass | 2026-10-29
DHR-TC05 | Deduplicate last-good updates for repeated/shared deploy units | 1. Execute a successful smoke fixture with migrate, import-data, repeated backend, and repeated frontend units. 2. Capture requested last-good writes. | Exactly one backend and one frontend last-good update are requested; migration/import units do not create extra runtime keys. | Exactly two fixture updates were requested: one backend key and one frontend key. | Pass | 2026-10-29
DHR-TC06 | Select the previous revision after smoke failure while preserving pipeline failure | 1. Make the initial curl fixture fail and the post-rollback fixture succeed. 2. Supply a valid, different previous SHA through fake Parameter Store. 3. Execute smoke-and-rollback.sh. 4. Inspect the submitted command, stderr, and exit status. | The rollback command targets the previous SHA; recovery is logged, but the failed deployment still exits nonzero and does not overwrite last-good. | One fixture SSM command selected the previous SHA. Recovery was logged, no last-good update was requested, and the script exited 1. No remote rollback occurred. | Pass | 2026-10-29
DHR-TC07 | Limit a frontend rollback to frontend runtime services | 1. Configure a failing initial smoke fixture, a successful recovery fixture, and DEPLOY_UNITS=frontend. 2. Inspect the generated remote command. | The command updates frontend with --no-deps and does not recreate backend. | The captured command included up -d --no-deps for frontend and no backend recreation. Execution of that remote command was simulated. | Pass | 2026-10-29
DHR-TC08 | Avoid rerunning migrations and data imports during rollback | 1. Configure smoke failure with DEPLOY_UNITS=migrate,import-data,backend. 2. Supply a valid previous SHA. 3. Inspect the rollback command. | Rollback restores the backend runtime only; it does not rerun migrate or import-data jobs. | One backend runtime command was requested. No run --rm migration/import command appeared. This does not prove database compatibility or data preservation. | Pass | 2026-10-29
DHR-TC09 | Fall back to a legacy last-good parameter when the component key is missing | 1. Make the component-specific Parameter Store lookup fail in the fixture. 2. Return a valid SHA from the legacy unsuffixed key. 3. Execute the failing-smoke scenario. | The script reads the legacy key and requests rollback to its valid previous revision. | Two lookups occurred in order, followed by one rollback command using the fixture previous SHA. | Pass | 2026-10-29
DHR-TC10 | Handle a missing previous deployment version safely | 1. Make the initial smoke check fail. 2. Make both component-specific and legacy last-good lookups fail. 3. Inspect exit status and requested remote commands. | Exit nonzero, report that no valid last-good revision exists, and do not request an unsafe rollback. | Script exited 1, logged that no valid last-good revision exists, and requested no remote command. | Pass | 2026-10-29
DHR-TC11 | Reject a malformed previous revision | 1. Fail the smoke fixture. 2. Return not-a-sha as the previous version. 3. Inspect script output and remote command requests. | The malformed revision is rejected; no deployment command is requested and the script remains failed. | Script exited 1, reported an invalid/missing last-good revision, and requested no remote command. | Pass | 2026-10-29
DHR-TC12 | Refuse a no-op rollback to the same failed revision | 1. Fail the smoke fixture. 2. Return the current failed SHA as the last-good SHA. 3. Inspect stderr and command requests. | The script explicitly refuses the no-op rollback, performs no remote deployment, and exits nonzero. | Script logged refusal of a no-op rollback, requested no remote command, and exited 1. | Pass | 2026-10-29
DHR-TC13 | Preserve failure when the rollback health check is also unhealthy | 1. Fail both initial and post-rollback curl fixtures. 2. Simulate successful execution of the rollback command. 3. Inspect the final message and exit status. | Report that rollback completed but its smoke check failed; do not claim healthy recovery or return success. | Script logged that the rollback smoke check failed and exited 1. Both HTTP outcomes and remote completion were fixtures. | Pass | 2026-10-29
DHR-TC14 | Attempt rollback when the deployment command itself fails | 1. Run deploy-with-rollback.sh. 2. Simulate Failed for the new-version SSM command and Success for the rollback command. 3. Inspect submitted revisions and final exit code. | The wrapper requests the current revision first, then the valid previous revision; it retains a nonzero exit status after the failed deployment. | Two commands were captured in the expected revision order. The wrapper logged a rollback attempt and exited 1. Post-rollback health was not checked by this wrapper test. | Pass | 2026-10-29
DHR-TC15 | Retain remote error evidence when rollback execution fails | 1. Fail the initial smoke fixture. 2. Simulate an SSM rollback failure with diagnostic output. 3. Inspect stderr, recovery messages, and final exit status. | The script includes the remote failure details, identifies the component rollback failure, omits a successful-recovery message, and exits nonzero. | Fixture remote failure details and backend rollback failure were retained in stderr; no successful-recovery message appeared; exit code was 1. | Pass | 2026-10-29
DHR-TC16 | Verify the deployed health endpoint is reachable and reports readiness | 1. Obtain the approved deployment URL and timestamped build identity. 2. Request GET /api/health through the actual public route with certificate verification enabled. 3. Record HTTP status, response body, and duration. 4. Confirm the model health-skip flag is not masking readiness. | The actual endpoint returns HTTP 200, status=ok, and model_ready=true within the agreed health-check budget; TLS validation succeeds. Evidence identifies environment and checked version. | Not executed: no deployment URL or live environment evidence was supplied. Isolated handler Pass results do not establish deployment availability. | Not executed | —
DHR-TC17 | Validate health degradation and recovery against a real inference dependency | 1. In an explicitly approved disposable staging environment, capture healthy output. 2. Make the inference dependency unavailable using the approved fault procedure. 3. Record HTTP 503 and unhealthy payload. 4. Restore the dependency and verify stable readiness. 5. Record checks for other required dependencies separately. | Health changes from ready to unhealthy and back to ready. Model checks are enabled. Database/search readiness is not inferred from this endpoint, which checks inference readiness rather than all application dependencies. | Not executed: no approved fault-injection environment was supplied. No running dependency was stopped or altered. | Not executed | —
DHR-TC18 | Verify the previous release and rollback prerequisites with read-only evidence | 1. Collect current and previous component Git SHAs from release records/last-good parameters. 2. Resolve the prior image digests and verify the artifacts still exist. 3. Compare with the currently running image identity. 4. Review rollback permissions, procedure, and database compatibility/backup evidence. | Previous revisions are valid, distinct from the failed release, available as immutable images, and compatible with rollback. The evidence identifies which components can be restored safely. | Not executed: fixture SHAs/digests are synthetic; actual release records, registry artifacts, permissions, and database compatibility were not inspected. | Not executed | —
DHR-TC19 | Demonstrate real rollback recovery and preserve application data | 1. Obtain explicit approval for a rollback drill on disposable staging. 2. Record current image digests, representative read-only application results, and test-data counts. 3. Execute the approved rollback to the prepared previous version. 4. Verify restored runtime SHA/digests and health repeatedly over the agreed observation window. 5. Recheck data and unaffected services. | Selected components run the prepared previous images; health remains stable; data and unaffected services are preserved. The failed release remains recorded as failed even if recovery succeeds. | Not executed: no live rollback was authorized or performed. Local command construction and simulated SSM success do not prove runtime version recovery or data safety. | Not executed | —
DHR-TC20 | Correlate and retain complete deployment health and rollback evidence | 1. Collect the real build URL/ID, environment, timestamps, failed and restored revisions/digests, component scope, health responses, SSM command result, and final pipeline status. 2. Correlate them to one rollout/rollback event. 3. Verify reviewer access and retention. 4. Check that secrets are absent from shared artifacts. | A reviewer can establish why rollback occurred, what actually ran before/after, whether recovery was healthy, and the final build outcome. Evidence is retained without exposed credentials or misleading success claims. | Not executed for a deployment event. Local JSON/logs contain fixture evidence only; no Jenkins/SSM event or deployed version was correlated and no live evidence retention policy was verified. | Not executed | —

## Scope and Evidence
Item | Details
Preconditions (user-stated) | Application is deployed; health check endpoints are available; previous deployment version and rollback procedures are prepared. Not independently verified.
Summary | 20 cases: 15 local component/fixture Pass, 5 live deployment cases Not executed. No real deployment health or rollback success is claimed.
Execution timestamp | 2026-10-29T12:13:05.250886+07:00
Repository HEAD | 9394a52058329a4917c5a39606cd63e0c30b8336
Test level | Local isolated route and shell fixture checks only. Model HTTP, curl and AWS/SSM are mocked. Full application, real HTTP transport, retries, real images and deployments not verified.
Safety | No deployment, Jenkins job, AWS call, live Parameter Store write, dependency outage, or real rollback was triggered. No application/pipeline code changed.
Missing live inputs | Approved deployment URL, actual current/previous revisions, immutable image identities, deployment event records and explicitly approved staging drill.
Health endpoint scope | Model/inference readiness only; does not independently verify database/search readiness. Full application startup was excluded from isolated route checks.
Synthetic fixtures | Previous SHA is 40 a characters; failed SHA is 40 b characters. These are not real deployed versions.
Local evidence | .amp/in/artifacts/health-rollback-results.json
Local evidence | .amp/in/artifacts/health-rollback-run.log
Local evidence | .amp/in/artifacts/run_health_rollback_checks.py
Cleanup | Temporary fixture directories removed; no remote resources created.